## Overview
WBS Dashboard Overview
Legend |  | Quick Stats
P0 | Critical path / release blocker | Total Work Packages
P1 | Important for MVP | Completed
P2 | Useful but non-blocking | In Progress
Blocked
Progress %
Abbreviations:
P0/P1/P2 = priority tier, RLS = Row Level Security, ETA = Estimated Time of Arrival, E2E = End-to-End

## WBS Tracker
Regional Tasting Shuttle MVP — Work Breakdown Structure
Designed for Excel + Google Sheets import ¦ Source: 2026-05-27 WBS
Phase | WP ID | Work Package | Description | Owner | Priority | Status | Depends On | Start (plan) | End (plan) | Acceptance Criteria | Notes
A | A1 | Tablet/Fully Kiosk runbook execution | Integrated device session for spikes 001/002/005/007 | Ops+Eng | P0 | Not Started | - | 2026-05-28 | 2026-05-29 | Field evidence captured and archived | Release gate
A | A2 | Launch gate decision | Go/No-Go and pivot freeze | Product | P0 | Not Started | A1 | 2026-05-29 | 2026-05-29 | Explicit signed decision | Blocker clear
B | B1 | Project scaffolding | React+Vite PWA shell, Supabase wiring | Frontend | P1 | Not Started | A2 | 2026-05-30 | 2026-05-31 | Shell compiles and env split verified | No service key frontend
B | B2 | Data model + migrations | Routes/stops/buses/drivers/assignments/stop_logs/daily_codes | Backend | P0 | Not Started | A2 | 2026-05-30 | 2026-06-01 | Migrations apply cleanly | Indexes included
B | B3 | RLS + RPC boundary | Driver scoped writes, admin scoped ops | Backend | P0 | Not Started | B2 | 2026-06-01 | 2026-06-02 | Policies enforce assignment boundary | Negative tests pass
B | B4 | Auth flows | Admin login + driver alias PIN/password flow | Backend+Frontend | P1 | Not Started | B3 | 2026-06-02 | 2026-06-03 | Driver/admin auth E2E works | Session UX clear
C | C1 | Driver session + preflight | PIN login and geolocation permission recovery | Frontend | P1 | Not Started | B4 | 2026-06-03 | 2026-06-04 | Denied-state recovery works | Tablet-first UX
C | C2 | Live location publisher | 3-5s Supabase Realtime Broadcast loop | Frontend | P0 | Not Started | B3 | 2026-06-04 | 2026-06-05 | Stable updates + stale state handling | Ephemeral only
C | C3 | Stop operations UI | Arrival confirm + boarded/alighted counters | Frontend | P1 | Not Started | C1 | 2026-06-04 | 2026-06-05 | Driver can submit stop event | Clear operator flow
C | C4 | Offline stop queue | IndexedDB queue + ordered replay + idempotency | Frontend | P0 | Not Started | C3 | 2026-06-05 | 2026-06-06 | No stop-log loss during short offline | Replay idempotent
D | D1 | Rider access flow | QR/deep-link + code entry + invalid handling | Frontend | P1 | Not Started | C2 | 2026-06-06 | 2026-06-07 | Rider can enter with valid code | Error copy clear
D | D2 | Live map experience | MapLibre + OpenFreeMap + provider config | Frontend | P1 | Not Started | D1 | 2026-06-07 | 2026-06-08 | Map loads and provider toggle works | No OSM prod traffic
D | D3 | Live shuttle + stops | Route/stops + active shuttle marker | Frontend | P0 | Not Started | C2 | 2026-06-08 | 2026-06-09 | Realtime marker + last seen state works | Usable on mobile
D | D4 | ETA module integration | Schedule + observed delay engine integration | Backend+Frontend | P1 | Not Started | B2,D3 | 2026-06-09 | 2026-06-10 | ETA shows with confidence state | Copy trustworthy
E | E1 | Ops CRUD | Routes/stops/buses/drivers/assignments management | Admin | P1 | Not Started | B2,B3 | 2026-06-10 | 2026-06-12 | Admin can configure operations | No code changes needed
E | E2 | Daily code operations | Generation + validation workflow | Admin | P1 | Not Started | E1 | 2026-06-12 | 2026-06-12 | Daily code lifecycle works | Simple controls
E | E3 | Live ops dashboard | Active buses + latest stop activity | Admin | P1 | Not Started | C2,C3 | 2026-06-12 | 2026-06-13 | Ops view reflects live state | Useful at a glance
E | E4 | Reporting | Daily totals + CSV export | Admin | P2 | Not Started | E3 | 2026-06-13 | 2026-06-14 | CSV export complete and accurate | Download tested
F | F1 | E2E scenario tests | Driver online/offline + rider + admin closeout | QA | P0 | Not Started | C,D,E | 2026-06-14 | 2026-06-15 | All critical scenarios pass | UAT ready
F | F2 | Observability + runbooks | Error logging + tablet recovery SOP | Ops | P1 | Not Started | F1 | 2026-06-15 | 2026-06-16 | Runbooks usable by operators | Telemetry in place
F | F3 | Launch checklist | Config/access/deploy smoke verification | Ops+Eng | P0 | Not Started | F2 | 2026-06-16 | 2026-06-16 | Launch checklist signed off | Go-live gate
Note on A4: Phase grouping for execution stream (A=Validation, B=Foundation, C=Driver, D=Rider, E=Admin, F=Hardening).
Note on B4: Unique work package ID used for tracking and dependency references.
Note on F4: Priority tier: P0=critical blocker, P1=important for MVP, P2=lower urgency.
Note on G4: Execution status: Not Started, In Progress, Blocked, Done.
Note on H4: Dependency IDs that must be completed first (comma-separated).
Note on K4: Clear definition of done for this work package; use measurable acceptance checks.
Note on F5: P0: Release blocker / critical path item.
Note on F6: P0: Release blocker / critical path item.
Note on F7: P1: Important for MVP completion.
Note on F8: P0: Release blocker / critical path item.
Note on F9: P0: Release blocker / critical path item.
Note on F10: P1: Important for MVP completion.
Note on F11: P1: Important for MVP completion.
Note on F12: P0: Release blocker / critical path item.
Note on F13: P1: Important for MVP completion.
Note on F14: P0: Release blocker / critical path item.
Note on F15: P1: Important for MVP completion.
Note on F16: P1: Important for MVP completion.
Note on F17: P0: Release blocker / critical path item.
Note on F18: P1: Important for MVP completion.
Note on F19: P1: Important for MVP completion.
Note on F20: P1: Important for MVP completion.
Note on F21: P1: Important for MVP completion.
Note on F22: P2: Nice-to-have, lower urgency.
Note on F23: P0: Release blocker / critical path item.
Note on F24: P1: Important for MVP completion.
Note on F25: P0: Release blocker / critical path item.

## Milestones
Delivery Milestones (M0-M5)
Milestone | Name | Target Date | Exit Criteria | Status | Notes
M0 | Field validation closeout | 2026-05-29 | A1/A2 complete with evidence | Not Started | P0 gate
M1 | Core platform + security baseline | 2026-06-03 | B1-B4 baseline complete | Not Started | RLS enforced
M2 | Driver ops end-to-end | 2026-06-06 | C1-C4 complete | Not Started | Offline resilience
M3 | Rider map + ETA end-to-end | 2026-06-10 | D1-D4 complete | Not Started | Mobile-first usability
M4 | Admin ops + reporting | 2026-06-14 | E1-E4 complete | Not Started | CSV export done
M5 | Hardening + launch readiness | 2026-06-16 | F1-F3 signoff | Not Started | Go-live ready

## Dependencies
Critical Dependencies
Dependency | Why it matters | Risk if delayed | Mitigation
B2/B3 -> C2/C4 | Schema/RLS before driver writes | Data integrity/security violations | Implement and test policy gates first
C2/C4 -> D3 | Rider marker depends on realtime + durable logs | Rider view becomes misleading | Use stale-state UX + replay validation
B2 -> D4 | ETA needs schedule + stop logs | ETA unavailable/inaccurate | Seed schedule and backfill test logs
C+D+E -> F1 | E2E tests require all surfaces | False confidence from partial testing | Block F1 until baseline complete

## Abbreviations
Abbreviations & Acronyms
Quick reference for terms used across Overview, WBS Tracker, Milestones, and Dependencies.
Abbreviation | Meaning | Context in this plan
WBS | Work Breakdown Structure | Hierarchy of phases and work packages for delivery planning.
MVP | Minimum Viable Product | Smallest launchable live-operations product that delivers core value.
P0 | Priority 0 (Critical) | Release blocker / critical path item that must be completed.
P1 | Priority 1 (Important) | Important for MVP completeness but not always a day-0 blocker.
P2 | Priority 2 (Nice-to-have) | Useful enhancement with lower urgency vs P0/P1.
RLS | Row Level Security | Supabase/Postgres policy layer controlling row-level read/write access.
RPC | Remote Procedure Call | Narrow backend database function endpoints for controlled operations.
ETA | Estimated Time of Arrival | Predicted next-stop timing shown to riders.
UAT | User Acceptance Testing | Pre-launch validation by real operators/users on realistic workflows.
SOP | Standard Operating Procedure | Operational runbook for repeatable driver/admin handling.
E2E | End-to-End | Tests covering complete workflow across frontend, backend, and data.
CSV | Comma-Separated Values | Export format for daily reports.
GPS | Global Positioning System | Source for live driver location updates.
PWA | Progressive Web App | Installable web app experience for driver/rider/admin surfaces.